## Sheet1
Task name | status | implementation effect | Algo owner | comments
JFIL confidence always FF | done | bug | Yoni | not a bug, result of JFIL bypass
Correlation bin size should be 22b instead of 21b | done | Design | Ohad | Doc change; ASIC need to review impact
DIGG traces - align between env/matlab | Done | ASICvalidation | Yoni
Add GENG bypass register with input linear transformation | done | Design | Ohad
GENG LUT for range finder mode | done | Design | Ohad | System bug
Invalidation trace in JFIL - IR output is wrong | Done | ASICvalidation | Yoni
Support registers of size 1-7 | Reject | Design | Ohad
RAST pixel FIFO PCQ trace | done | ASICvalidation | Vitali
RAST filter traces | done | ASICvalidation | Vitali
validation: range finder |  | validation | Ohad
Validation: multi focal |  | validation | Ohad
Validation: DIGG |  | validation
Validation: RAST |  | validation
Validation: DCOR |  | validation
Validation: DEST |  | validation
Validation: JFIL edge |  | validation | Yoni
Validation: JFIL sort |  | validation | Yoni
validation: JFIL edge |  | validation
validation: JFIL gradient |  | validation
validation: JFIL geometric |  | validation | Noa
Validation: JFIL bilateral |  | validation | Vitali
Notch filter locations bug |  | firmware | Yoni
Notch filter variable bandwidth |  | firmware | Yoni
CBUF x release LUT |  | firmware
ROI FOV adjustment |  | firmware
RX/TX propogation delay |  | firmware
DCOR mask changes | done | Design | Yoni | ASIC requirement
CMA filter mux 2:1 optimization (left-right symmetry utilization) | done | Design | Vitali | ASIC requirement ;
PLL frequency dependant sample distnace | Done | firmware | Ohad
select DCOR possible working modes based on coarse cor max size, and hw clocks | Table done | ASICvalidation |  | Need to add FW constraints
DEST add temperature depndent scale shift | done | Design |  | Default : scale-1 Shift-0
Packer (ROI) | done | Design |  | New unit
Packer (privacy mode support) | done | Design |  | Create a new block
NEST as IR output NEST on IR channel (DCOR) | done | Design | Vitali | Debug
PCQ chunk FIFO bug fix | done | Design |  | Matlab bug
Jfil_features_depth_out Jfil_features_ir_out | Done | ASICvalidation
cma debug (DCOR) | done | Design | Vitali | pass CMA slice according to a register to the IR
corr debug (DEST) | done | design | Yoni | pass 20b of acor rslice according to a register to depth+conf, corroffset in IR
gamma swap | done | design
STAT dependencies | done | design | Aviad
STAT small image | done | design | Aviad
DIGG ang2xy added registers | done | design | Ohad
trace log |  | ASICvalidation | Noa